## Sheet1
ID | VST ID | TASK | BUG | POSSIBLE | SENSE? | PLANNED | Until | DATE | Remarks | OOS | Out Of Sprint
1 |  | entry field for Modell Number | no | yes | no | NP | 2017-01-22 | 2017-12-22 |  | NP | Not yet planned
2 | 463 | Promotion - Which Promotion? | no | yes | yes | Sprint 4 | 2017-01-22 | 2017-12-22 | Basic Promoliste in Dialog
3 |  | own entry field for Suggestions | no | yes | no | NP | 2017-01-22 | 2017-12-22 |  | Sprint | from | to
4 |  | Umlaute wie z.B. "Beschaedigt" | yes | yes | yes | OOS | 2017-12-22 | 2017-12-22 |  | 4 | 2017-12-22 | 2017-01-21
5 | 465 | Preview not editable | yes | yes | yes | OOS | 2017-01-22 | 2017-12-22 | The preview will be overwritten. Even if the agent was writing something in it | 5 | 2017-01-22 | 2017-03-21
6 | 466 | Additional Description | yes | yes | yes | OOS | 2017-01-22 | 2017-12-27 | Using of TextViews instead of Textfields | 6 | 2017-04-22 | 2017-05-21
7